Ministry of Environment and Energy

Design and Build of Coastal Protection Structures at Hulhudhoo

(AGR) 438-ECAS/PRIV/2016/88

# Monthly Progress Report – August

Report No

1

01st August 2017 – 31st August 2017

Report No 5

Presented by: Contractor, RR Maldives (Pvt) Ltd

Presented to: Project Engineer, Ministry of Environment and Energy

Date: 07th September 2017

Contents

# Report No

5

CONTENTS

- Project Details

- Project Background

2.1 Scope of Work

2.2 Site Layout Plan

- Site Organisation Chart

- Details of Bonds and Guarantees

- Details of Payments

- Program and Progress

6.1 Master Programme

6.2 Review of Project Progress against the programme

6.3 Layout View of Progress

- Resources – Manpower and Machinery & Vehicle

- Weather Record

- Issues and Public Complaints

- Progress Photographs

## Document Control

Document Storage

Document Title: 	Design and Build of Coastal Protection Structures at S. Hulhudhoo

Author:	 		Pabasara Kalansooriya

Last Updated:		07/09/2017

Last Saved by: 	Pabasara Kalansooriya

Version Control Log

| Version | Author | Description of Changes | Date | Signature |
| --- | --- | --- | --- | --- |
| V0-00 | Pabasara Kalansooriya, Assistant Engineer (Head Office) | Initial Draft | 07/09/2017 |  |
| V0-01 | Ranjith Senadhera, Project Coordinator | Review and final Adjustments | 07/09/2017 |  |

Document Circulation

| Organization | Designation | Name |
| --- | --- | --- |
| Ministry of Environment and Energy | Minister of State | Mr. Abdulla Ziyad |
| Ministry of Environment and Energy | Assistant Director | Mr. Mohamed Ibrahim Jaleel |
| Ministry of Environment and Energy |  | Mr. Mohamed Zahir |
| Ministry of Environment and Energy |  | Mr. Ahamed Hassaan Zuhair |
| Ministry of Environment and Energy |  | Mr. Liusha Mohamed |
| Ministry of Environment and Energy |  | Mr. Aishath Huma |

- Project Details

| Project Name | Design and Build of Coastal Protection Structures at S. Hulhudhoo |
| --- | --- |
| Employer | Ministry of Environment and Energy, Green Building, Maafannu, Male’, 20392, Republic of Maldives. |
| Engineer | Ministry of Environment and Energy, Green Building, Maafannu, Male’, 20392, Republic of Maldives. |
| Contractor | RR Maldives Pvt Ltd |
| Contract Amount | MVR 24,446,024.96 with GST |
| Commencement | 27th November 2016 |
| Construction period | 368 Days from the day of signing the contract |
| Scheduled date of completion | 30th November 2017 |
| Defects Liability | 365 days |
| Retention | 5% of the certified work done Limit of retention - 5% of the Accepted Contract Price |

2.0 	Project Background

2.1 Scope of Work

The government of Maldives wishes to build rock boulder revetments along the eroding shoreline of S. Hulhudhoo that are subjected to severe erosion.

The scope of works of the project is:

- Design and construction of rock boulder revetment to an extent of 1.3km north the existing seawall on the South - East side of the island which was built in 2008;

- Repairing the damaged areas of 452m seawall built on the south side of the island.

RR Maldives Pvt Ltd has undertaken the all the works as the main Contractor.

2.2 Site Layout Plan

Figure 2.2 – Site Layout (Pink Line indicate the area proposed for new revetment and green line indicate the existing seawall)

3.0 Site Organization Chart

4.0 Details of Bonds, Insurance and Guarantees

| No | Description | Bond/Policy No | Value with GST (MVR) | Provider Name | Validity Period |
| --- | --- | --- | --- | --- | --- |
| 1 | Performance Guarantee | LG/MVR/228/2016 | 1,410,124.33 | Allied Insurance Company Male | 27-11-2016 31-12-2017 |
| 2 | Advance Payment Guarantee | LG/MVR/244/2016 | 3,391,368.56 | BOC Male | 26-12-2016 25-12-2017 |

5.0 Details of Payment

Progress of payments against is as follows.

| No | Payment Description | Submitted |  | Certified |  | Cumulative Received Amount (MVR) with GST |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Date | Amount (MVR) with GST | Date | Amount (MVR) with GST |  |
| 1 | Advance Payment | 26-12-2016 | 3,391,368.56 | 15-02-2017 | 3,391,368.56 | 3,391,368.56 |
| 2 | IPA - 01 | 15-05-2017 | 2,715,807.91 | 31-05-2017 | 2,715,807.91 | 6,107,176.47 |
| 3 | IPA - 02 | 15-05-2017 | 2,106,973.87 | 31-05-2017 | 2,106,973.87 | 8,214,150.35 |
| 4 | IPA - 03 | 02-06-2017 | 525,057.30 | 14-06-2017 | 525,057.30 | 8,739,207.64 |
| 5 | IPA - 04 | 19-06-2017 | 592,485.22 | 20-07-2017 | 592,485.22 | 9,331,692.86 |
| 6 | IPA - 05 | 22-06-2017 | 1,936,772.65 | 20-07-2017 | 1,936,772.65 | 11,268,465.51 |
| 7 | IPA - 06 | 02-08-2017 | 595,255.07 | 23-08-2017 | 595,255.07 | 11,863,720.58 |
| 8 | IPA - 07 | 15-08-2017 | 1,895,689.59 |  |  |  |
| 9 | IPA - 08 | 31-08-2017 | 676,017.70 |  |  |  |

### 6.0 Program and Progress

6.1 Master Programme

6.2 Review of Project Progress against the Programme

| Evaluation as at | 31st August 2017 |
| --- | --- |
| Master Programme | Revision 01 |
| Contract Period | 368 Days |
| Elapsed Time | 277 Days |
| Remaining Time | 91 days |

| Item | Description | As per Programme |  | Physical Progress |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Start | Finish | Estimated | Actual |
| 01 | Temporary Jetty for Rock Barge | 04.02.2017 | 15.02.2017 | 100% | 100% |
| 02 | Delivery of Rock Armours at Site | 03.04.2017 | 18.05.2017 | 100% | 100% |
| 03 | Sand Dredging and Transport | 02.04.2017 | 28.09.2017 | 84% | 75% |
| 04 | Revetment Construction | 19.05.2017 | 20.11.2017 | 56% | 40% |
| 05 | Rectification of Existing Seawall | 03.07.2017 | 31.08.2017 | 100% | 75% |
| 06 | Bathing Steps Construction | 01.09.2017 | 25.09.2017 | 00% | 50% |
|  | Total Work |  |  | 81% | 74% |

6.3 Layout View of Progress

### 7.0 Resources Manpower and Machinery

8.0 Weather Record

9.0 Issues and Public Complaints

9.1 Contract Issues

No any issues up to now

9.2 Public Complaints

No any public complaints up to now

- Progress Photographs

| Progress Photos – August 2017 |  |
| --- | --- |
| Third Rock Barge (Photo I) | Unload rocks from Barge (Photo II) |
| Dredged Sand Supply to Revetment (Photo III) | Fill for Revetment (Photo IV) |
| Sand Layer Compaction (Photo V) | Excavation for Toe (Photo VI) |
| Sand Bedding (Photo VII) | Level Checking (Photo VIII) |
| Laying Geo Textile (Photo IX) | Boulder Placing at Toe (Photo X) |
| Secondary Armour Layer Placing (Photo XI) | Primary Armour Placing (Photo XII) |
| Crest Geo Textile Preparation (Photo XIII) | Crest Rock Armour Placing (Photo XIV) |
| Final Back Filling (Photo XV) | Completed Revetment (Photo XVI) |
| Excavation for Existing Sea Wall Toe Beam (Photo XVII) | Cleaning & Washing for Toe Beam (Photo XVIII) |
| Formwork for Toe Beam (Photo XIX) | Using RO Plant Water for Concrete (Photo XX) |
| Concrete Mixing (Photo XXI) | Concrete Levelling (Photo XXII) |
| Curing in Toe Beam (Photo XXIII) | After removal of Formwork (Photo XXIV) |
| Cube Cast for Quality Check (Photo XXV) | Slump Test (Photo XXVI) |
| Overtop on Existing Sea Wall (Photo XXVII) | Drilling Holes for Dowelling (Photo XXVIII) |
| Dowel Fixing for Curtain Wall (Photo XXIX) | Formwork for Curtain Wall (Photo XXX) |
| Concrete Pouring for Curtain Wall (Photo XXXI) | Compaction of Concrete using Porker (Photo XXXII) |
| Rectified Sea Wall Top (Photo XXXIII) | Rectified Sea Wall at Side (Photo XXXIV) |